{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["专项（项目）资金绩效自评表","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"专项（项目）资金绩效自评表","index":0,"n_rows":37,"n_cols":8,"rows_kept":37,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,36,0],[15,1,30,1],[15,2,20,2],[22,2,23,2],[24,2,30,2],[31,1,34,1],[35,1,36,1]],"flags":["formulas_cached_only"]}
["附件3"]
["2020年度专项（第七次全国人口普查）资金绩效自评表"]
["（2020年度）"]
[]
["专项（项目）名称",null,null,"第七次全国人口普查"]
["项目主管单位",null,null,"盐边县统计局"]
["项目实施单位",null,null,"盐边县统计局"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",144,144,100]
[{"$nulls":3},"       其中：上级财政资金",77,77,100]
[{"$nulls":3},"             本级财政资金",67,67,100]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,0,null,null,"  通过户口整顿、清查摸底、入户登记等工作，并进行数据处理。全面查清全县人口数量、结构、分布、城乡住房等方面情况，准确、及时掌握全县人口数量、分布、结构及发展变化情况。为各级党委、政府制定国民经济和社会发展计划提供可靠数据支撑和信息参考。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标","“两员”报酬","普查指导员和普查员的报酬","支付普查指导员和普查员的报酬77万元。",{"v":1,"d":"100%"}]
[{"$nulls":3},"普查人员培训","对普查指导员及普查员进行培训","分批对12个乡镇901人“两员”开展培训",{"v":1,"d":"100%"}]
[{"$nulls":3},"宣传工作","印制宣传资料及横幅","印制宣传资料及横幅",{"v":1,"d":"100%"}]
[{"$nulls":3},"人员聘用","招聘普查办公室人员","招聘普查办公室人员6名",{"v":1,"d":"100%"}]
[{"$nulls":3},"办公费","普查所需办公用品","购置了普查所需办公用品",{"v":1,"d":"100%"}]
[{"$nulls":3},"差旅费","参加省、市培训以及对乡镇开展指导督查的差旅费","普查工作人员参加省、市培训以及对乡镇开展指导督查",{"v":1,"d":"100%"}]
[null,null,"质量指标","根据工作要求","工作推进顺利。全面、准确、及时地掌握全县人口数量、公布、结构情况。","工作推进顺利。全面、准确、及时地掌握全县人口数量、公布、结构情况。",{"v":1,"d":"100%"}]
[null,null,"时效指标","普查人员培训","预计2020年9月","2020-09-01",{"v":1,"d":"100%"}]
[{"$nulls":3},"入户登记完成时间","预计2020年底","2020年底",{"v":1,"d":"100%"}]
[null,null,"成本指标","“两员”报酬","77万元","77万元",{"v":1,"d":"100%"}]
[{"$nulls":3},"普查人员培训","8.51万元","8.51万元",{"v":1,"d":"100%"}]
[{"$nulls":3},"宣传工作","11.26万元","11.26万元",{"v":1,"d":"100%"}]
[{"$nulls":3},"人员聘用","20.47万元","20.47万元",{"v":1,"d":"100%"}]
[{"$nulls":3},"办公费","14.99万元","14.99万元",{"v":1,"d":"100%"}]
[{"$nulls":3},"差旅费","2.25万元","2.25万元",{"v":1,"d":"100%"}]
[{"$nulls":3},"印刷费","9.52万元","9.52万元",{"v":1,"d":"100%"}]
[null,"项目效益","经济效益\n指标","普查数据资料","依据普查数据资料科学制定国民经济和社会发展规划，推动经济高质量发展。","已完成",{"v":1,"d":"100%"}]
[null,null,"社会效益\n指标","发布普查主要数据","全面、准确、及时地发布全县人口数量、公布、结构情况，为各级党委、政府科学决策和部门管理提供数据支撑和信息参考。","已完成",{"v":1,"d":"100%"}]
[null,null,"生态效益\n指标","普查数据资料","完善人口发展战略和政策体系，促进人口长期均衡发展。","已完成",{"v":1,"d":"100%"}]
[null,null,"可持续影响\n指标","普查数据资料","全面、准确、及时地发布全县人口数量、公布、结构情况，为各级党委、政府科学决策和部门管理提供数据支撑和信息参考。","已完成",{"v":1,"d":"100%"}]
[null,"满意度指标","满意度指标","服务对象满意度","抽样调查达到基本满意及以上","抽样调查达到基本满意及以上",{"v":1,"d":"100%"}]
[null,null,"……"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}