{"text_format":"3","workbook":"xls","n_sheets":5,"sheets":["专项（新冠状病毒肺炎疫情防控春风行动）资金绩效自评表","专项（新型冠状病毒感染的肺炎防控工作经费）资金绩效自评表 ","专项（项目）资金绩效自评表","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"专项（新冠状病毒肺炎疫情防控春风行动）资金绩效自评表","index":0,"n_rows":45,"n_cols":8,"rows_kept":45,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,44,0],[15,1,27,1],[15,2,17,2],[18,2,20,2],[21,2,23,2],[24,2,26,2],[28,1,40,1],[28,2,30,2],[31,2,33,2],[34,2,36,2],[37,2,39,2],[41,1,44,1],[41,2,43,2]],"flags":["formulas_cached_only"]}
["附件3"]
["2020年度专项（项目）资金绩效自评表"]
["（2020年度）"]
[]
["专项（项目）名称",null,null,"新冠状病毒肺炎疫情防控春风行动补助资金"]
["项目主管单位",null,null,"盐边县交通运输局"]
["项目实施单位"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：","2.3567万元","2.3567万元",100]
[{"$nulls":3},"       其中：上级财政资金"]
[{"$nulls":3},"             本级财政资金","2.3567万元","2.3567万元",100]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"\n专项用于盐边县新型冠状病毒肺炎疫情防控期间执行“春风行动”任务客运企业补助经费，疫情期间安全有序的将我县返岗农民工运输至务工城市，在疫情防控时期统筹做好防控工作和农民工返岗运输服务。",null,null,"盐边县新型冠状病毒肺炎疫情防控期间执行“春风行动”任务客运企业补助经费，疫情期间安全有序的将我县返岗农民工运输至务工城市，在疫情防控时期统筹做好防控工作和农民工返岗运输服务。取得了良好的社会效益，提高了群众满意度。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：","运输趟次8次","8次",100]
[{"$nulls":3}," 指标2：","运输车辆5辆","5辆",100]
[{"$nulls":3}," ……","运输人数147人","147人",100]
[null,null,"质量指标"," 指标1：","疫情期间安全有序的将我县返岗农民工运输至务工城市","基本达到预期指标",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：","返岗农民工到达务工城市及时率","基本达到预期指标",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1：","不超出县人社局向县政府提交的预算数","基本达到预期指标",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：","疫情期间安全有序的将我县返岗农民工运输至务工城市","基本达到预期指标",100]
[{"$nulls":3}," 指标2：","对本地务工输出人员起到有效防控作用","基本达到预期指标",100]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：","巩固疫情防控成效","基本达到预期指标",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：","本地务工输出人员疫情期间提供安全、便捷、快速的出行服务","基本达到预期指标",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]

{"sheet":"专项（新型冠状病毒感染的肺炎防控工作经费）资金绩效自评表 ","index":1,"n_rows":45,"n_cols":8,"rows_kept":45,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,44,0],[15,1,27,1],[15,2,17,2],[18,2,20,2],[21,2,23,2],[24,2,26,2],[28,1,40,1],[28,2,30,2],[31,2,33,2],[34,2,36,2],[37,2,39,2],[41,1,44,1],[41,2,43,2]],"flags":["formulas_cached_only"]}
["附件3"]
["2020年度专项（项目）资金绩效自评表"]
["（2020年度）"]
[]
["专项（项目）名称",null,null,"根据盐财资预【2020】8号下达新型冠状病毒感染的肺炎防控相关工作保障经费"]
["项目主管单位",null,null,"盐边县交通运输局"]
["项目实施单位"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：","1万元","1万元",100]
[{"$nulls":3},"       其中：上级财政资金"]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金","1万元","1万元",100]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"根据疫情防控工作指南，加强疫情防控宣传，储备必备的口罩、酒精等防控物资，做好疫情防控工作。",null,null,"我单位根据疫情防控工作指南，加强疫情防控宣传，储备必备的口罩、酒精等防控物资，做好疫情防控工作，对疫情防控工作起到了一定的社会作用。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：","持续保障日常工作开展所需必须数量的口罩、酒精等","基本达到预期指标",100]
[{"$nulls":3}," 指标2：","可正常使用体温枪一个","1个",100]
[{"$nulls":3}," ……","宣传工作所需的展板、宣传资料","基本达到预期指标",100]
[null,null,"质量指标"," 指标1：","防疫物资符合质量标准","质检合格",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：","疫情防控工作开展期间","2020年",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1：","防控工作经费1万元","1万元",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：","提高疫情防控意识","基本达到预期指标",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1：","阻碍疫情传播","基本达到预期指标",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：","疫情防控常态化","基本达到预期指标",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：","群众满意度","基本达到预期指标",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]

{"sheet":"专项（项目）资金绩效自评表","index":2,"n_rows":45,"n_cols":8,"rows_kept":45,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,44,0],[15,1,27,1],[15,2,17,2],[18,2,20,2],[21,2,23,2],[24,2,26,2],[28,1,40,1],[28,2,30,2],[31,2,33,2],[34,2,36,2],[37,2,39,2],[41,1,44,1],[41,2,43,2]],"flags":["formulas_cached_only"]}
["附件3"]
["2020年度专项（项目）资金绩效自评表"]
["（2020年度）"]
[]
["专项（项目）名称",null,null,"盐边县客运枢纽项目"]
["项目主管单位",null,null,"盐边县交通运输局"]
["项目实施单位",null,null,"盐边县交通建设投资经营有限责任公司"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",2500]
[{"$nulls":3},"       其中：上级财政资金",2500,1939.4,78]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"我县拟建的二级客运站枢纽，紧靠成昆铁路复线盐边客运站并与之成形配套，成昆铁路复线建成通车后，该站客流将辐射凉山州的会理、会东、盐源及云南的华坪、永仁等地。项目总投资7175.94万元，其中3505.13万元为征地拆迁费和场平建设费，工程建设费用及其他费用按3670.81万元控制，计划2020年主体结构出来",null,null,"我县拟建的二级客运站枢纽，紧靠成昆铁路复线盐边客运站并与之成形配套，成昆铁路复线建成通车后，该站客流将辐射凉山州的会理、会东、盐源及云南的华坪、永仁等地。项目总投资7175.94万元，其中3505.13万元为征地拆迁费和场平建设费，工程建设费用及其他费用按3670.81万元控制。该项目现已全面完工，主体结构已出。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：","主体结构一座","一座",95]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"质量指标"," 指标1：","主体结构合格","基本达到预期",95,"待主体分部工程质量验收报告后确认"]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：","2020年全年","2020年全年",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：","提高运输能力",null,0,"工程未完工"]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：","提升对外交通便利",null,0,"工程未完工"]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：","人民群众满意度",null,50,"工程未完工"]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]

{"sheet":"Sheet2","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":4,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}