{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["专项（项目）资金绩效自评表","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"专项（项目）资金绩效自评表","index":0,"n_rows":46,"n_cols":8,"rows_kept":46,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,45,0],[15,1,28,1],[15,2,18,2],[19,2,21,2],[22,2,24,2],[25,2,27,2],[29,1,41,1],[29,2,31,2],[32,2,34,2],[35,2,37,2],[38,2,40,2],[42,1,45,1],[42,2,44,2]],"flags":["formulas_cached_only"]}
["附件3"]
["2020年度专项（项目）资金绩效自评表"]
["（2020年度）"]
[]
["专项（项目）名称",null,null,"箐河中心校新建综合楼"]
["项目主管单位",null,null,"盐边县教育和体育局"]
["项目实施单位",null,null,"盐边县永兴镇中心学校"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",288,87.1401,30.26]
[{"$nulls":3},"       其中：上级财政资金",288,87.1401,30.26]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"\n\n箐河中心学校新建综合楼\n\n2020年全年我校项目收入总额为288万元",null,null,"完成施工图全部内容：盐边县箐河傈僳族乡中心学校综合楼新建一栋，建筑面积744.52平方米建筑三层，因学校场地受限与原有教学楼贴临建设并借用原有教学楼楼梯吉行疏散。其中一层为通道、学生宿舍（2间）男女生卫生间及男女生水浴室，二、三层为学生宿舍（8间）及卫生间。室外工程：包含外地坪及新建消防水池等内容\n"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：","永兴镇中心幼儿园外墙安全隐患排除；"]
[{"$nulls":3}," 指标2：","盐边县箐河傈僳族乡中心学校综合楼新建一栋","建筑面积744.52平方米建筑三层，因学校场地受限与原有教学楼贴临建设并借用原有教学楼楼梯吉行疏散。其中一层为通道、学生宿舍（2间）男女生卫生间及男女生水浴室，二、三层为学生宿舍（8间）及卫生间。室外工程：包含外地坪及新建消防水池等内容",30.26,"工程已完工、未审计。施工方未提供支付凭证"]
[{"$nulls":4},"永兴镇中心学校新建综合教学楼"]
[{"$nulls":3}," 指标3："]
[null,null,"质量指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[]
[null,null,"时效指标"," 指标1：","项目建成后，改善了学校学生多，教室紧张的局面，减少大班额，达到教学要求大纲",100,100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1：","工程项目均按预算成本进行","是","是"]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：","在项目实施过程中为节约成本，降低环境污染环境，施工中采取废水回收沉定再次利用，废旧垃圾运到统一销毁处理，很好的保护了生态环境，为可持续发展提供了有力保障，减轻学生就近入学负担，为家庭节约开支，提到了社会及家长的好评。","提高了教育教学质量",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：","体现政策导向，长期保障教育教学工作持续发展，保障广大师生的生命安全。","2020年部门支出为我校各项工作正常运转。"]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：","得到社会的一致好评，小学六年级学生升率较高，部份学生考上了理想的中学",null,100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}