{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["专项（项目）资金绩效自评表 (2)","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"专项（项目）资金绩效自评表 (2)","index":0,"n_rows":225,"n_cols":8,"rows_kept":225,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,44,0],[15,1,27,1],[15,2,17,2],[18,2,20,2],[21,2,23,2],[24,2,26,2],[28,1,40,1],[28,2,30,2],[31,2,33,2],[34,2,36,2],[37,2,39,2],[41,1,44,1],[41,2,43,2],[46,0,46,7],[47,0,47,7],[49,0,49,2],[49,3,49,7],[50,0,50,2],[50,3,50,7],[51,0,51,2],[51,3,51,7],[52,0,56,2],[52,6,52,7],[53,6,53,7],[54,6,54,7],[55,6,55,7],[56,6,56,7],[57,0,58,0],[57,1,57,3],[57,4,57,7],[58,1,58,3],[58,4,58,7],[59,0,89,0],[60,1,72,1],[60,2,62,2],[63,2,65,2],[66,2,68,2],[69,2,71,2],[73,1,85,1],[73,2,75,2],[76,2,78,2],[79,2,81,2],[82,2,84,2],[86,1,89,1],[86,2,88,2],[91,0,91,7],[92,0,92,7],[94,0,94,2],[94,3,94,7],[95,0,95,2],[95,3,95,7],[96,0,96,2],[96,3,96,7],[97,0,101,2],[97,6,97,7],[98,6,98,7],[99,6,99,7],[100,6,100,7],[101,6,101,7],[102,0,103,0],[102,1,102,3],[102,4,102,7],[103,1,103,3],[103,4,103,7],[104,0,134,0],[105,1,117,1],[105,2,107,2],[108,2,110,2],[111,2,113,2],[114,2,116,2],[118,1,130,1],[118,2,120,2],[121,2,123,2],[124,2,126,2],[127,2,129,2],[131,1,134,1],[131,2,133,2],[136,0,136,7],[137,0,137,7],[139,0,139,2],[139,3,139,7],[140,0,140,2],[140,3,140,7],[141,0,141,2],[141,3,141,7],[142,0,146,2],[142,6,142,7],[143,6,143,7],[144,6,144,7],[145,6,145,7],[146,6,146,7],[147,0,148,0],[147,1,147,3],[147,4,147,7],[148,1,148,3],[148,4,148,7],[149,0,179,0],[150,1,162,1],[150,2,152,2],[153,2,155,2],[156,2,158,2],[159,2,161,2],[163,1,175,1],[163,2,165,2],[166,2,168,2],[169,2,171,2],[172,2,174,2],[176,1,179,1],[176,2,178,2],[181,0,181,7],[182,0,182,7],[184,0,184,2],[184,3,184,7],[185,0,185,2],[185,3,185,7],[186,0,186,2],[186,3,186,7],[187,0,191,2],[187,6,187,7],[188,6,188,7],[189,6,189,7],[190,6,190,7],[191,6,191,7],[192,0,193,0],[192,1,192,3],[192,4,192,7],[193,1,193,3],[193,4,193,7],[194,0,224,0],[195,1,207,1],[195,2,197,2],[198,2,200,2],[201,2,203,2],[204,2,206,2],[208,1,220,1],[208,2,210,2],[211,2,213,2],[214,2,216,2],[217,2,219,2],[221,1,224,1],[221,2,223,2]],"flags":["formulas_cached_only"]}
[]
["2020年度专项资金绩效自评表"]
["（2020年度）"]
[]
["专项（项目）名称",null,null,"第四批新购普通商品住房购房补贴资金"]
["项目主管单位",null,null,"盐边县住房和城乡建设局"]
["项目实施单位",null,null,"盐边县住房和城乡建设局"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",238.57,238.57,100]
[{"$nulls":3},"       其中：上级财政资金"]
[{"$nulls":3},"             本级财政资金",238.57,238.57,100]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"支付2018年263户购房户申请领取购房补贴且符合条件的补贴资金，享受1%的84户，享受2%的60户，享受3.5%的18户，享受5%的101户\n",null,null,"支付2018年263户购房户申请领取购房补贴且符合条件的补贴资金，享受1%的84户，享受2%的60户，享受3.5%的18户，享受5%的101户\n"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：","263户购房户","全部完成",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"质量指标"," 指标1：","申请领取购房补贴且符合条件的购房户","已达到",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：","2020全年","部分完成",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1：",238.57,238.57,100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1：","申请领取购房补贴且符合条件的263户购房户","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：","通过项目的实施，确保资金使用效率，保障各项工作进展顺利，为群众服好务。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1：","通过项目实施，改善人居环境。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：","体现政策导向，长期保障工作平稳进行。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：","通过项目实施，力争使服务对象对住建局工作满意度达到较好水平。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[]
["2020年度专项资金绩效自评表"]
["（2020年度）"]
[]
["专项（项目）名称",null,null,"第五批新购普通商品住房购房补贴资金"]
["项目主管单位",null,null,"盐边县住房和城乡建设局"]
["项目实施单位",null,null,"盐边县住房和城乡建设局"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",154.53,154.53,100]
[{"$nulls":3},"       其中：上级财政资金"]
[{"$nulls":3},"             本级财政资金",154.53,154.53,100]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"支付2018年107户购房户申请领取购房补贴且符合条件的补贴资金，享受1%的3户，享受2%的15户，享受3.5%的1户，享受4.55%的1户，享受5%的87户\n",null,null,"支付2018年107户购房户申请领取购房补贴且符合条件的补贴资金，享受1%的3户，享受2%的15户，享受3.5%的1户，享受4.55%的1户，享受5%的87户\n\n"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：","107户购房户","全部完成",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"质量指标"," 指标1：","申请领取购房补贴且符合条件的购房户","已达到",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：","2020全年","部分完成",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1：",154.53,154.53,100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1：","申请领取购房补贴且符合条件的107户购房户","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：","通过项目的实施，确保资金使用效率，保障各项工作进展顺利，为群众服好务。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1：","通过项目实施，改善人居环境。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：","体现政策导向，长期保障工作平稳进行。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：","通过项目实施，力争使服务对象对住建局工作满意度达到较好水平。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[]
["2020年度专项资金绩效自评表"]
["（2020年度）"]
[]
["专项（项目）名称",null,null,"第六批新购普通商品住房购房补贴资金"]
["项目主管单位",null,null,"盐边县住房和城乡建设局"]
["项目实施单位",null,null,"盐边县住房和城乡建设局"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",342.01,342.01,100]
[{"$nulls":3},"       其中：上级财政资金"]
[{"$nulls":3},"             本级财政资金",342.01,342.01,100]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"支付2018年255户购房户申请领取购房补贴且符合条件的补贴资金，享受1%的55户，享受2%的18户，享受3.5%的6户，享受5%的176户\n",null,null,"支付2018年255户购房户申请领取购房补贴且符合条件的补贴资金，享受1%的55户，享受2%的18户，享受3.5%的6户，享受5%的176户\n\n"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：","255户购房户","全部完成",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"质量指标"," 指标1：","申请领取购房补贴且符合条件的购房户","已达到",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：","2020全年","部分完成",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1：",342.01,342.01,100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1：","申请领取购房补贴且符合条件的255户购房户","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：","通过项目的实施，确保资金使用效率，保障各项工作进展顺利，为群众服好务。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1：","通过项目实施，改善人居环境。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：","体现政策导向，长期保障工作平稳进行。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：","通过项目实施，力争使服务对象对住建局工作满意度达到较好水平。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[]
["2020年度专项资金绩效自评表"]
["（2020年度）"]
[]
["专项（项目）名称",null,null,"农村危房改造项目"]
["项目主管单位",null,null,"盐边县住房和城乡建设局"]
["项目实施单位",null,null,"盐边县住房和城乡建设局"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",527.4,500.39,95]
[{"$nulls":3},"       其中：上级财政资金",527.4,500.39,95]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"2019-2020年盐边县农村危房改造跨年度任务数1074户（其中，三类重点对象624户、非建档立卡边缘户293户、建档立卡贫困户维修加固及未享受政策增加建档立卡户危房改造157户）\n",null,null,"   1.农村危房改造。2019-2020年盐边县农村危房改造跨年度任务数1074户（其中，三类重点对象624户、非建档立卡边缘户293户、建档立卡贫困户维修加固及未享受政策增加建档立卡户危房改造157户）"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：","2020年农村危房改造项目","部分完成",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"质量指标"," 指标1：","达到工程质量等指标要求","已达到",90]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：","2020年全年","部分完成",90]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1：",527.4,500.39,95,"项目没验收，未达到资金拨付要求"]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1：","   1.农村危房改造。2019-2020年盐边县农村危房改造跨年度任务数1074户（其中，三类重点对象624户、非建档立卡边缘户293户、建档立卡贫困户维修加固及未享受政策增加建档立卡户危房改造157户）","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：","通过项目的实施，确保资金使用效率，保障各项工作进展顺利，为群众服好务。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1：","通过项目实施，改善人居环境。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：","体现政策导向，长期保障工作平稳进行。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：","通过项目实施，力争使服务对象对住建局工作满意度达到较好水平。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[]
["2020年度专项资金绩效自评表"]
["（2020年度）"]
[]
["专项（项目）名称",null,null,"农村危房改造项目专项工作经费"]
["项目主管单位",null,null,"盐边县住房和城乡建设局"]
["项目实施单位",null,null,"盐边县住房和城乡建设局"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",15,15,100]
[{"$nulls":3},"       其中：上级财政资金"]
[{"$nulls":3},"             本级财政资金",15,15,100]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"保证2019-2020年盐边县农村危房改造项目工作按质按量完成。",null,null,"保证2019-2020年盐边县农村危房改造项目工作按质按量完成。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：","2020年农村危房改造项目专项工作经费","部分完成",100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"质量指标"," 指标1：","工作按质按量完成","已达到",90]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：","2020年全年","部分完成",90]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1：",15,15,100]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1：","   1.保证农村危房改造工作按质按完成","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：","通过项目的实施，确保资金使用效率，保障各项工作进展顺利，为群众服好务。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1：","通过项目实施，改善人居环境。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：","体现政策导向，长期保障工作平稳进行。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：","通过项目实施，力争使服务对象对住建局工作满意度达到较好水平。","已达到",{"v":0.95,"d":"95%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}