{"text_format":"3","workbook":"xls","n_sheets":5,"sheets":["专项（抗疫特别国债）资金绩效自评表","专项（医疗服务与保障能力提升）资金绩效自评表","专项（传染病防治、疫情防控）资金绩效自评表","专项（事业）资金绩效自评表","Sheet2"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"专项（抗疫特别国债）资金绩效自评表","index":0,"n_rows":45,"n_cols":8,"rows_kept":45,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,44,0],[15,1,27,1],[15,2,17,2],[18,2,20,2],[21,2,23,2],[24,2,26,2],[28,1,40,1],[28,2,30,2],[31,2,33,2],[34,2,36,2],[37,2,39,2],[41,1,44,1],[41,2,43,2]],"flags":["formulas_cached_only"]}
["附件2"]
["专项（项目）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"抗疫特别国债资金"]
["项目主管单位",null,null,"盐边县卫生健康局"]
["项目实施单位",null,null,"盐边县人民医院"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",1950,1373.104,{"v":0.7042,"d":"70.42%"}]
[{"$nulls":3},"       其中：上级财政资金",1950,1373.104,{"v":0.7042,"d":"70.42%"}]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"改建医技综合楼及配套设施完善、改建两间核酸检测实验室",null,null,"进行医技综合楼包括检验科、血透室ICU、手术室综合项目装修及采购相应设备，按照资金拨付及项目合同进度进行核酸检测实验室建设"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：医技楼装修及设备采购","≥90%",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：核酸检测实验室改建","≥90%",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," ……"]
[null,null,"质量指标","指标1：提升疾病诊疗救治能力","≥90%",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：提高实验室检测水平","≥90%",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：项目资金按要求及时拨付。","及时支付",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标","指标1："]
[{"$nulls":3}," 指标2：提高核酸检测能力"]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：改善检验科、ICU等基础设施薄弱条件","得到改善","得到改善",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：达到核酸检测实验室。具备检测能力","得到提高","得到提高",{"v":1,"d":"100%"}]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：重点人群满意度","≥90%",{"v":0.95,"d":"95%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]

{"sheet":"专项（医疗服务与保障能力提升）资金绩效自评表","index":1,"n_rows":45,"n_cols":8,"rows_kept":45,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,44,0],[15,1,27,1],[15,2,17,2],[18,2,20,2],[21,2,23,2],[24,2,26,2],[28,1,40,1],[28,2,30,2],[31,2,33,2],[34,2,36,2],[37,2,39,2],[41,1,44,1],[41,2,43,2]],"flags":["formulas_cached_only"]}
["附件2"]
["专项（项目）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"医疗服务与保障能力提升（公立医院改革）"]
["项目主管单位",null,null,"盐边县卫健局"]
["项目实施单位",null,null,"盐边县人民医院"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",130.67,94.37,{"v":0.7222,"d":"72.22%"}]
[{"$nulls":3},"       其中：上级财政资金",130.67,94.37,{"v":0.7222,"d":"72.22%"}]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"受新型冠状肺炎病毒疫情影响，提高医院快速检测核酸的能力；改善医院就诊环境，提高病人就诊舒适度。",null,null,"已完成核酸快检设备采购、验收并投入使用。逐步改善医院就诊环境，病人满意度得到提升。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：完成核酸快检设备采购","≥80%",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：核酸快检设备投入使用","≥80%",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标3：改善医院就诊环境","≥80%",{"v":0.85,"d":"85%"},{"v":1,"d":"100%"}]
[null,null,"质量指标"," 指标1：提升核酸检测能力","得到提升","得到提升",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：提供疫情防控保障","得到提高","得到提高",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标3：改善医院就诊环境","得到改善","得到改善",{"v":1,"d":"100%"}]
[null,null,"时效指标"," 指标1：项目资金按照进度及时支付","在项目采购完成并验收后按照合同支付","核酸快检设备已按照合同进度完成支付",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：受益群众对项目的满意度","≥90%",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：改善医疗就诊条件，增强医疗诊治能力","≥80%",{"v":0.9,"d":"90%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：重点人群满意度","≥90%",{"v":0.95,"d":"95%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]

{"sheet":"专项（传染病防治、疫情防控）资金绩效自评表","index":2,"n_rows":45,"n_cols":8,"rows_kept":45,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,44,0],[15,1,27,1],[15,2,17,2],[18,2,20,2],[21,2,23,2],[24,2,26,2],[28,1,40,1],[28,2,30,2],[31,2,33,2],[34,2,36,2],[37,2,39,2],[41,1,44,1],[41,2,43,2]],"flags":["formulas_cached_only"]}
["附件2"]
["专项（项目）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"传染病防治、新型冠状病毒疫情防控"]
["项目主管单位",null,null,"盐边县卫健局"]
["项目实施单位",null,null,"盐边县人民医院"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",31.15,31.15,{"v":1,"d":"100%"}]
[{"$nulls":3},"       其中：上级财政资金"]
[{"$nulls":3},"             本级财政资金",31.15,31.15,{"v":1,"d":"100%"}]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"\n全面落实HIV抗体试剂采购、传染病信息报告管理，预防控制措施，提高发现率，扩大治疗覆盖面；开展疫情防控所需要的设备、核酸试剂和防控物资保障采购。",null,null,"完成HIV抗体检测人数8371人次、传染病检测人数7526人次；完成疫情防控物资、核酸试剂、设备的采购保障。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：HIV抗体检测覆盖率",{"v":0.9,"d":"90%"},{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：传染病治疗覆盖率",{"v":0.95,"d":"95%"},{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标3：新冠疫情核酸检测覆盖率",{"v":0.95,"d":"95%"},{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[null,null,"质量指标"," 指标1：感染者/病人随访检测比例",{"v":0.92,"d":"92%"},{"v":0.95,"d":"95%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：抗病毒治疗成功率",{"v":0.94,"d":"94%"},{"v":0.98,"d":"98%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标3：新冠疫情核酸试剂储备率",{"v":0.98,"d":"98%"},{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[null,null,"时效指标"," 指标1：长期","延续实施","按时完成",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：常态化疫情防控","常态化管理","按时完成",{"v":1,"d":"100%"}]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1：HIV抗体检测费用及工作经费","9.36万",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：传染病治疗工作经费","7.16万",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标3：新冠肺炎核酸检测经费","14.63万",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：艾滋病患者规范管理率","≥90%",{"v":0.98,"d":"98%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：精准防控，疫情控制在可控范围内","常态化管理",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：服务对象满意率",{"v":0.95,"d":"95%"},{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]

{"sheet":"专项（事业）资金绩效自评表","index":3,"n_rows":45,"n_cols":8,"rows_kept":45,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,44,0],[15,1,27,1],[15,2,17,2],[18,2,20,2],[21,2,23,2],[24,2,26,2],[28,1,40,1],[28,2,30,2],[31,2,33,2],[34,2,36,2],[37,2,39,2],[41,1,44,1],[41,2,43,2]],"flags":["formulas_cached_only"]}
["附件2"]
["专项（项目）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"盐边县人民医院事业发展基金"]
["项目主管单位",null,null,"盐边县卫健局"]
["项目实施单位",null,null,"盐边县人民医院"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",3182.71,3182.71,{"v":1,"d":"100%"}]
[{"$nulls":3},"       其中：上级财政资金"]
[{"$nulls":3},"             本级财政资金",3182.71,3182.71,{"v":1,"d":"100%"}]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"\n加强和规范收支预算管理，合理控制成本，提高管理水平，提高资源使用效率。",null,null,"按照本年度事业收入总数全额上缴，加强和规范收支管理。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：事业收入全额上缴率",{"v":1,"d":"100%"},{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"质量指标"," 指标1：及时入上缴率",{"v":1,"d":"100%"},{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：规范管理率",{"v":1,"d":"100%"},{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：2021年度","年度内","年度内",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1："]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]

{"sheet":"Sheet2","index":4,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}