{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["专项（项目）资金绩效自评表","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"专项（项目）资金绩效自评表","index":0,"n_rows":26,"n_cols":8,"rows_kept":26,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,25,0],[15,1,21,1],[15,2,16,2],[17,2,18,2],[20,2,21,2],[22,1,23,1],[24,1,25,1]],"flags":["formulas_cached_only"]}
["附件3"]
["2021年度专项（粮食畜牧业调查）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"粮食畜牧业调查"]
["项目主管单位",null,null,"盐边县统计局"]
["项目实施单位",null,null,"盐边县统计局"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：",3.49,3.49,{"v":1,"d":"100%"}]
[{"$nulls":3},"       其中：上级财政资金"]
[{"$nulls":3},"             本级财政资金",3.49,3.49,{"v":1,"d":"100%"}]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"实行粮食、畜牧业统计调查数据归口管理将有利于加快建立现代化农业统计调查体系，有利于为党和政府提供更加完整、及时、真实、准确的“三农”统计调查数据，有利于提高政府统计公信力。为各项工作推动提供重要数据支撑。",null,null,"该项目属国家常规统计调查工作， 10月25日前完成粮食抽样调查10个点的现场实割实测工作。12月25日前完成26户的畜牧业抽样调查工作，并根据实际情况对调查数据进行收集、整理、审核、汇总、评估和上报, 确保每一个环节规范统一。全年完成了粮食、畜牧业统计调查工作信息2篇，经济快讯4篇, 2021年盐边县农村经济运行分析3篇,生猪调研报告1篇。 2021年盐边县粮食畜牧业抽样监测调查获四川调查总队“粮食调查先进县”、攀枝花调查队“生猪调查先进县”、攀枝花调查队“粮食调查先进县”，3名辅助调查员获“全省优秀辅助调查员”，4名辅助调查员获“粮食调查先进个人”，3名辅助调查员获“生猪调查先进个人”荣誉称号。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标","调查员业务培训","全年调查员培训2次","全年调查员培训2次",{"v":1,"d":"100%"}]
[{"$nulls":3},"调查员劳务","18个调查员劳务费","18个调查员劳务费",{"v":1,"d":"100%"}]
[null,null,"质量指标"," 圆满完成粮食调查工作","粮食抽样调查10个点的现场实割实测工作。","10月25日前完成粮食抽样调查10个点的现场实割实测工作。"]
[{"$nulls":3}," 圆满完成牧业调查工作","26户的畜牧业抽样调查工作，并根据实际情况对调查数据进行收集、整理、审核、汇总、评估和上报, 确保每一个环节规范统一。","12月25日前完成26户的畜牧业抽样调查工作，并根据实际情况对调查数据进行收集、整理、审核、汇总、评估和上报, 确保每一个环节规范统一。",{"v":1,"d":"100%"}]
[null,null,"时效指标"," 按工作计划","2021年1月至12月","2021年1月至12月"]
[null,null,"成本指标","培训费","0.2万元","0.2万元",{"v":1,"d":"100%"}]
[{"$nulls":3},"劳务费","3.29万元","3.29万元",{"v":1,"d":"100%"}]
[null,null,"社会效益\n指标","调查数据","为党和政府提供更加完整、及时、真实、准确的“三农”统计调查数据，有利于提高政府统计公信力。","已完成",{"v":1,"d":"100%"}]
[null,null,"可持续影响\n指标","调查数据","粮食畜牧业统计调查数据实行归口管理是贯彻落实党的十九大精神和党中央、国务院关于统计改革重大决策部署要求的重要措施，是完善统计调查体系的迫切要求，是新形势下国家统计调查事业发展的重要内容。","已完成",{"v":1,"d":"100%"}]
[null,"满意度指标","满意度指标","服务对象满意度","抽样调查达到基本满意及以上","抽样调查达到基本满意及以上",{"v":1,"d":"100%"}]
[null,null,"……"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}