{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["专项（项目）资金绩效自评表","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"专项（项目）资金绩效自评表","index":0,"n_rows":45,"n_cols":8,"rows_kept":45,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,44,0],[15,1,27,1],[15,2,17,2],[18,2,20,2],[21,2,23,2],[24,2,26,2],[28,1,40,1],[28,2,30,2],[31,2,33,2],[34,2,36,2],[37,2,39,2],[41,1,44,1],[41,2,43,2]],"flags":["formulas_cached_only"]}
[]
["2021年度专项（项目）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"校园安全辅助服务人员服务费"]
["项目主管单位",null,null,"盐边县教育和体育局"]
["项目实施单位",null,null,"盐边县虹翔保安服务有限责任公司"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：","427.68万元","427.68万元",{"v":1,"d":"100%"}]
[{"$nulls":3},"       其中：上级财政资金"]
[{"$nulls":3},"             本级财政资金","427.68万元","427.68万元",{"v":1,"d":"100%"}]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"对全县23个中心学校进行全年安保服务。",null,null,"已完成目标。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标"," 指标1：全县中小学校、幼儿园","全县23个中心校（包括部分村小）、幼儿园1所","全县23个中心校（包括部分村小）、幼儿园1所",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：每人每月3330元","427.68万元","427.68万元",{"v":1,"d":"100%"}]
[{"$nulls":3}," ……"]
[null,null,"质量指标"," 指标1：有效防范各类涉校案件和暴恐袭击事件，保障师生生命财产安全","全县23个中心校（包括部分村小）、幼儿园1所","全县23个中心校（包括部分村小）、幼儿园1所",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"时效指标"," 指标1：每天24小时值班值守","2021年1-12月","2021年1-12月",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"成本指标"," 指标1：每人每月3300元","35.964万元","35.964万元",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"项目效益","经济效益\n指标"," 指标1：保安人员服务费","427.68万元","427.68万元",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：人数X标准X月+其它"]
[{"$nulls":3}," ……"]
[null,null,"社会效益\n指标"," 指标1：收益学生、家长","≧23000人","≧23000人",{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2：学校（园）"]
[{"$nulls":3}," ……"]
[null,null,"生态效益\n指标"," 指标1：生活质量提升"]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"可持续影响\n指标"," 指标1：教育发展占位"]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]
[null,"满意度指标","满意度指标"," 指标1：全县中小学校、幼儿园","满意度≧95%",{"v":0.95,"d":"95%"},{"v":1,"d":"100%"}]
[{"$nulls":3}," 指标2："]
[{"$nulls":3}," ……"]
[null,null,"……"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}