{"text_format":"3","workbook":"xls","n_sheets":5,"sheets":["盐边县中学校新建初中部教学楼工程项目","盐边县中学校乡村学校少年宫运转资金","盐边县中学校学生营养改善计划项目","盐边县中学校高考考点防暑降温系统建设安装工程","特殊教育学生公用经费直达资金"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"盐边县中学校新建初中部教学楼工程项目","index":0,"n_rows":25,"n_cols":8,"rows_kept":25,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,24,0],[15,1,18,1],[19,1,21,1],[20,2,21,2],[22,1,23,1],[22,2,23,2]],"flags":["formulas_cached_only"]}
["附件2"]
["专项（项目）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"盐边县中学校新建初中部教学楼工程项目"]
["项目主管单位",null,null,"盐边县教育和体育局"]
["项目实施单位",null,null,"盐边县中学校"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：","1026.07万元","635.3955万元",{"v":0.6193,"d":"61.93%"}]
[{"$nulls":3},"       其中：上级财政资金","1026.07万元","635.3955万元",{"v":0.6193,"d":"61.93%"}]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"通过项目实施，改善学校办学条件，提升学校办学品位，保障学校教育教学工作的正常开展、顺利完成了2021年度的教育教学任务，完成实施项目预算数1026.07万元。",null,null,"项目正在稳步实施中尚未完工，实际完成支付数635.3955万元，完成率61.93%。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标","完成盐边县中学校新建初中部教学楼工程项目，完成项目资金1026.07万元","1026.07万元","635.3955万元",{"v":0.6193,"d":"61.93%"},"工程项目尚未完工"]
[null,null,"质量指标","完成盐边县中学校新建初中部教学楼工程项目","完成盐边县中学校新建初中部教学楼工程项目","按工作计划完成61.93%","已完成61.93%","工程项目尚未完工"]
[null,null,"时效指标","按工作计划"," 2021年1月—12月","达到预期指标","已完成61.93%","工程项目尚未完工"]
[null,null,"成本指标","完成项目资金1026.07万元","完成项目资金1026.07万元支付","635.3955万元","已完成61.93%","工程项目尚未完工"]
[null,"项目效益","经济效益\n指标"]
[null,null,"社会效益\n指标","提高盐边县中学校办学质量，提升办学品位，让3470名学生及200多名教职员工受益，取得良好的办学效益和社会效益","提高盐边县中学校办学质量，提升办学品位，让3470名学生及200多名教职员工受益，取得良好的办学效益和社会效益","按工作计划完成61.93%","已完成61.93%","工程项目尚未完工"]
[]
[null,"满意度指标","满意度指标","服务对象满意度","广大师生及家长达到基本满意及以上。","基本达到预期指标","已完成年度目标任务"]
[{"$nulls":3},"群众满意度","全县广大人民群众达到基本满意及以上","基本达到预期指标","已完成年度目标任务"]
[{"$nulls":3}," ……"]

{"sheet":"盐边县中学校乡村学校少年宫运转资金","index":1,"n_rows":25,"n_cols":8,"rows_kept":25,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,24,0],[15,1,18,1],[19,1,21,1],[20,2,21,2],[22,1,23,1],[22,2,23,2]],"flags":["formulas_cached_only"]}
["附件2"]
["专项（项目）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"盐边县中学校乡村学校少年宫运转资金"]
["项目主管单位",null,null,"盐边县教育和体育局"]
["项目实施单位",null,null,"盐边县中学校"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：","4.7万元","4.7万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"       其中：上级财政资金","4.7万元","4.7万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null," 该项目的实施保障学校乡村少年宫相关活动的正常开展，从而顺利完成了 2021 年度的乡村少年宫活动任务，全部完成实施项目预算数4.7万",null,null,"该项目的实施保障学校乡村少年宫相关活动的正常开展，从而顺利完成了 2021 年度的乡村少年宫活动任务。 实际完成实施数4.7万元，完成率100%。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标","完成项目资金4.7万元","4.7万元","4.7万元",{"v":1,"d":"100.00%"}]
[null,null,"质量指标","开展教育教学工作，顺利完成教育教学目标任务。","完成乡村少年宫教育教学目标任务","按工作计划完成100%","已完成100%"]
[null,null,"时效指标","按工作计划"," 2021年1月—12月","达到预期指标","已完成100%"]
[null,null,"成本指标","完成项目资金4.7万元","完成项目资金4.7万元支付","4.7万元","已完成100%"]
[null,"项目效益","经济效益\n指标"]
[null,null,"社会效益\n指标","提高我校乡村少年宫服务质量，取得良好的办学效益和社会效益","提高我校乡村少年宫服务质量，取得良好的办学效益和社会效益","按工作计划完成100%","已完成100%"]
[]
[null,"满意度指标","满意度指标","服务对象满意度","广大师生达到95%满意及以上。","师生满意度98%","已完成年度目标任务"]
[{"$nulls":3},"群众满意度","全县广大人民群众达到95%满意及以上","满意度98%","已完成年度目标任务"]
[{"$nulls":3}," ……"]

{"sheet":"盐边县中学校学生营养改善计划项目","index":2,"n_rows":26,"n_cols":8,"rows_kept":26,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,25,0],[15,1,19,1],[15,2,16,2],[20,1,22,1],[21,2,22,2],[23,1,24,1],[23,2,24,2]],"flags":["formulas_cached_only"]}
["附件2"]
["专项（项目）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"盐边县中学校学生营养改善计划项目"]
["项目主管单位",null,null,"盐边县教育和体育局"]
["项目实施单位",null,null,"盐边县中学校"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：","68.17万元","68.17万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"       其中：上级财政资金","68.17万元","68.17万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null," 全面落实我校800多名义务教育学生的营养餐改善计划，切实提高了我校学生的营养水平和身体素质。全部完成实施项目预算数68.17万元",null,null,"我校所有义务教育学生全面实施营养改善计划，营养水平和身体素质得到全面提高，全年预算数68.17万元，实际完成实施数,68.17万元，完成率100%。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标","完成项目资金68.17万元","68.17万元","68.17万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"完成教育教学任务","完成本年度教育教学任务","已完成本年度教育教学任务",{"v":1,"d":"100.00%"}]
[null,null,"质量指标","开展教育教学工作，顺利完成教育教学目标任务。","完成乡村少年宫教育教学目标任务","按工作计划完成100%","已完成100%"]
[null,null,"时效指标","按工作计划"," 2021年1月—12月","达到预期指标","已完成100%"]
[null,null,"成本指标","完成项目资金68.17万元","完成项目资金68.17万元支付","68.17万元","已完成100%"]
[null,"项目效益","经济效益\n指标"]
[null,null,"社会效益\n指标","提高我校办学质量，让盐边县中学校成为盐边人民满意的学校","提高我校办学质量，让盐边县中学校成为盐边人民满意的学校","按工作计划完成100%","已完成100%"]
[]
[null,"满意度指标","满意度指标","服务对象满意度","义务教育阶段学生达到95%满意及以上。","义务教育阶段学生95%","已完成年度目标任务"]
[{"$nulls":3},"群众满意度","全县广大人民群众达到95%满意及以上","满意度98%","已完成年度目标任务"]
[{"$nulls":3}," ……"]

{"sheet":"盐边县中学校高考考点防暑降温系统建设安装工程","index":3,"n_rows":26,"n_cols":8,"rows_kept":26,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,25,0],[15,1,19,1],[15,2,16,2],[20,1,22,1],[21,2,22,2],[23,1,24,1],[23,2,24,2]],"flags":["formulas_cached_only"]}
["附件2"]
["专项（项目）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"盐边县中学校高考考点防暑降温系统建设安装工程"]
["项目主管单位",null,null,"盐边县教育和体育局"]
["项目实施单位",null,null,"盐边县中学校"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：","298.2万元","298.2万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"       其中：上级财政资金","298.2万元","298.2万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null," 改善了我校的办学条件，提升了我校的办学品位。全部完成实施项目预算数298.2万元",null,null,"采购了136台3匹风管式中央空调；10台5匹风管式中央空调；1套630KV箱式变电扩容设备及相关配套工程。改善了我校的办学条件，提升了我校的办学品位。全年预算数298.2万元，实际完成实施数,298.2万元，完成率100%。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标","完成项目资金298.2万元","298.2万元","298.2万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"完成教育教学任务","完成本年度教育教学任务","已完成本年度教育教学任务",{"v":1,"d":"100.00%"}]
[null,null,"质量指标","开展教育教学工作，顺利完成教育教学目标任务。","完成乡村少年宫教育教学目标任务","按工作计划完成100%","已完成100%"]
[null,null,"时效指标","按工作计划"," 2021年1月—12月","达到预期指标","已完成100%"]
[null,null,"成本指标","完成项目资金298.2万元","完成项目资金298.2万元支付","298.2万元","已完成100%"]
[null,"项目效益","经济效益\n指标"]
[null,null,"社会效益\n指标","提高我校办学质量，让盐边县中学校成为盐边人民满意的学校","提高我校办学质量，让盐边县中学校成为盐边人民满意的学校","按工作计划完成100%","已完成100%"]
[]
[null,"满意度指标","满意度指标","服务对象满意度","师生满意度达到95%以上","师生满意度达到96%","已完成年度目标任务"]
[{"$nulls":3},"群众满意度","全县广大人民群众达到95%满意及以上","满意度98%","已完成年度目标任务"]
[{"$nulls":3}," ……"]

{"sheet":"特殊教育学生公用经费直达资金","index":4,"n_rows":26,"n_cols":8,"rows_kept":26,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[4,0,4,2],[4,3,4,7],[5,0,5,2],[5,3,5,7],[6,0,6,2],[6,3,6,7],[7,0,11,2],[7,6,7,7],[8,6,8,7],[9,6,9,7],[10,6,10,7],[11,6,11,7],[12,0,13,0],[12,1,12,3],[12,4,12,7],[13,1,13,3],[13,4,13,7],[14,0,25,0],[15,1,19,1],[15,2,16,2],[20,1,22,1],[21,2,22,2],[23,1,24,1],[23,2,24,2]],"flags":["formulas_cached_only"]}
["附件2"]
["专项（项目）资金绩效自评表"]
["（2021年度）"]
[]
["专项（项目）名称",null,null,"特殊教育学生公用经费直达资金"]
["项目主管单位",null,null,"盐边县教育和体育局"]
["项目实施单位",null,null,"盐边县中学校"]
["项目资金\n（万元）",{"$nulls":3},"全年预算数","实际完成数","执行率（%）"]
[{"$nulls":3}," 年度资金总额：","7.8万元","7.8万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"       其中：上级财政资金","7.8万元","7.8万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"             本级财政资金"]
[{"$nulls":3},"             其他资金"]
["总\n体\n目\n标","年度设定目标",null,null,"实际完成情况"]
[null,"对我校13名特殊教育学生开展教育教学工作，保障学校工作的正常开展、完成 2021年度的教育教学目标任务。 全部完成实施项目预算数7.8万元",null,null,"对我校13名特殊教育学生开展教育教学工作，保障学校工作的正常开展、完成 2021年度的教育教学目标任务。全年预算数7.8万元，实际完成实施数7.8万元，完成率100%。"]
["绩\n效\n指\n标","一级\n指标","二级指标","三级指标","年度指标值","实际完成数","完成率（%）","未完成原因和改进措施"]
[null,"项目完成","数量指标","完成项目资金7.8万元","7.8万元","7.8万元",{"v":1,"d":"100.00%"}]
[{"$nulls":3},"完成教育教学任务","完成本年度教育教学任务","已完成本年度教育教学任务",{"v":1,"d":"100.00%"}]
[null,null,"质量指标","开展教育教学工作，顺利完成教育教学目标任务。","完成乡村少年宫教育教学目标任务","按工作计划完成100%","已完成100%"]
[null,null,"时效指标","按工作计划"," 2021年1月—12月","达到预期指标","已完成100%"]
[null,null,"成本指标","完成项目资金7.8万元","完成项目资金7.8万元支付","7.8万元","已完成100%"]
[null,"项目效益","经济效益\n指标"]
[null,null,"社会效益\n指标","提高我校办学质量，让盐边县中学校成为盐边人民满意的学校","提高我校办学质量，让盐边县中学校成为盐边人民满意的学校","按工作计划完成100%","已完成100%"]
[]
[null,"满意度指标","满意度指标","服务对象满意度","13名特殊教育学生满意度达到100%","13名特殊教育学生满意度达到100%","已完成年度目标任务"]
[{"$nulls":3},"群众满意度","全县广大人民群众达到96%满意及以上","满意度98%","已完成年度目标任务"]
[{"$nulls":3}," ……"]