{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["自评表","纵向"],"read":"whole","date_system":"1900"}

{"sheet":"自评表","index":0,"n_rows":32,"n_cols":11,"rows_kept":32,"merged":[[0,0,0,3],[0,5,0,7],[1,0,1,10],[2,0,2,1],[2,2,2,10],[3,0,3,1],[3,2,3,6],[3,8,3,10],[4,0,6,0],[4,1,5,1],[4,2,4,6],[4,7,4,10],[5,2,5,6],[5,7,5,10],[6,2,6,10],[7,0,12,0],[7,4,7,6],[8,4,8,6],[8,10,12,10],[9,4,9,6],[10,4,10,6],[11,4,11,6],[12,4,12,6],[13,0,26,0],[14,1,23,1],[14,2,21,2],[27,0,27,7],[28,1,28,10],[29,1,29,10],[30,1,30,10],[31,0,31,4],[31,5,31,10]]}
["报表编号：510000_0013zp"]
["部门预算项目支出绩效自评表（2024年度）"]
["项目名称",null,"51042224T000010504237-党政机构改革和事业单位机构改革经费"]
["主管部门",null,"中共盐边县委机构编制委员会办公室（部门）",{"$nulls":4},"实施单位 （盖章）","中共盐边县委机构编制委员会办公室"]
["项目基本情况","1.项目年度目标完成情况","项目年度目标",{"$nulls":4},"年度目标完成情况"]
[null,null,"完成14家党政机构改革工作任务（机构撤、并、建，“三定”核定）。完成224家事业单位改革工作任务（机构机构撤、并、建，“三定”核定）。构建简约高效的机构运行模式，节约行政成本。",{"$nulls":4},"全面完成党政机构改革工作任务，完成224家事业单位改革前期摸底调研数据及工作底稿制定。以保障大局为重心，重点领域为突破，积极助力共同富裕试验区典型经验探索实践，全力统筹编制资源蓄势赋能推动高质量发展，节约行政成本。"]
[null,"2.项目实施内容及过程概述","深入学习贯彻习近平总书记关于深化党和国家机构改革的重要论述和批示指示精神，全面完成党政机构改革，调整优化重点领域机构职能、持续深化行政执法体制改革、健全完善乡镇机构管理体制、精简规范设置议事协调机构，进一步优化调整事业单位职能编制和管理体制，着力健全完善优化协同高效的机构职能体系。"]
["预算执行情况（10分）","年度预算数（万元）","年初预算","调整后预算数","预算执行数",null,null,"预算执行率","权重","得分","原因"]
[null,"总额",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},null,null,{"v":1,"d":"100.00%"},10,10]
[null,"其中：财政资金",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},null,null,{"v":1,"d":"100.00%"},"/","/"]
[null,"财政专户管理资金",{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"单位资金",{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"其他资金",{"$nulls":6},"/","/"]
["绩效指标（90分）","一级指标","二级指标","三级指标","指标性质","指标值","度量单位","完成值","权重","得分","未完成原因分析"]
[null,"产出指标","数量指标","开展机构编制执行情况及使用效益评估","＝","2","家",2,"5",5]
[{"$nulls":3},"完成事业单位改革","＝","224","家",224,"10",10]
[{"$nulls":3},"完成党政机构改革","＝","14","家",14,"15",15]
[{"$nulls":3},"开展乡镇机构编制事项调研","＝","12","家",12,"5",5]
[{"$nulls":3},"完成机构编制数据核查","＝","291","家",291,"3",3]
[{"$nulls":3},"承办编委会议","≥","5","次",5,"5",5]
[{"$nulls":3},"外出考察培训","≥","5","次",5,"5",5]
[{"$nulls":3},"开展机构编制业务交流磋商会议","≥","30","次",30,"5",5]
[null,null,"质量指标","各项业务 办结","＝","100","%",100,"5",5]
[null,null,"时效指标","截止2024年底","＝","2024","年",2024,"2",5]
[null,"效益指标","社会效益指标","构建简约高效的机构运行模式，节约行政成本","定性","好",null,"好","20",20]
[null,"满意度指标","服务对象满意度指标","机构编制工作满意度测评","≥","95","%",98,"5",5]
[null,"成本指标","经济成本指标","资金支付金额","＝","10","万元",10,"5",5]
["合计",{"$nulls":7},100,100]
["评价结论","经项目实施业务部门综合自评，自评得分100分。该项目圆满完成各项预订目标，协同高效的机构职能体系得以进一步健全优化。"]
["存在问题","1.绩效评价工作有待进一步加强。由于县委编办人员较少，近期改革任务重，导致业务股室人员因忙业务而轻财政绩效评价工作参与，财政绩效评价指标体系细化不精准，业务股室参与度不高。\n2.受主客观因素制约，财务人员业务水平有待进一步提升。财务软件更新快，财政业务涉及知识范围广、要求高、时间急、任务重，单位财务人员年龄偏大，眼睛视力不好，加上患有慢性基础疾病，接受新知识，掌握新本领的能力不足。\n\n"]
["改进措施","1.加强全员财政法律法规的学习培训，切实提高全体职工对绩效评价工作的重视性和参与度。\n2.合理调整单位工作岗位布局，加强财务工作新老衔接“传帮带”过渡，为提高单位财务工作质量切实提供人力保障。\n"]
["项目负责人：孟剑",{"$nulls":4},"财务负责人：田明君"]

{"sheet":"纵向","index":1,"n_rows":4,"n_cols":7,"rows_kept":4,"merged":[[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,1,6]]}
[]
["部门代码","部门名称","单位代码","单位名称","一般公共预算"]
[{"$nulls":4},"年初预算数","调整后预算数","支付数"]
["258","中共盐边县委机构编制委员会办公室（部门）","258001","中共盐边县委机构编制委员会办公室",{"v":10,"d":"10.00"},{"v":10,"d":"10.00"},{"v":10,"d":"10.00"}]