{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":115,"n_cols":11,"rows_kept":115,"merged":[[1,0,1,10],[2,0,2,1],[2,2,2,10],[3,0,3,1],[3,2,3,6],[3,8,3,10],[4,0,6,0],[4,1,5,1],[4,2,4,6],[4,7,4,10],[5,2,5,6],[5,7,5,10],[6,2,6,10],[7,0,12,0],[7,4,7,6],[8,4,8,6],[8,10,12,10],[9,4,9,6],[10,4,10,6],[11,4,11,6],[12,4,12,6],[13,0,27,0],[14,1,20,1],[14,2,18,2],[23,1,27,1],[23,2,27,2],[28,0,28,7],[29,1,29,10],[30,1,30,10],[31,1,31,10],[32,0,32,4],[32,5,32,10],[35,0,35,10],[36,0,36,1],[36,2,36,10],[37,0,37,1],[37,2,37,6],[37,8,37,10],[38,0,40,0],[38,1,39,1],[38,2,38,6],[38,7,38,10],[39,2,39,6],[39,7,39,10],[40,2,40,10],[41,0,46,0],[41,4,41,6],[42,4,42,6],[42,10,46,10],[43,4,43,6],[44,4,44,6],[45,4,45,6],[46,4,46,6],[47,0,55,0],[48,1,51,1],[48,2,49,2],[54,1,55,1],[54,2,55,2],[56,0,56,7],[57,1,57,10],[58,1,58,10],[59,1,59,10],[60,0,60,4],[60,5,60,10],[65,0,65,10],[66,0,66,1],[66,2,66,10],[67,0,67,1],[67,2,67,6],[67,8,67,10],[68,0,70,0],[68,1,69,1],[68,2,68,6],[68,7,68,10],[69,2,69,6],[69,7,69,10],[70,2,70,10],[71,0,76,0],[71,4,71,6],[72,4,72,6],[72,10,76,10],[73,4,73,6],[74,4,74,6],[75,4,75,6],[76,4,76,6],[77,0,83,0],[78,1,80,1],[78,10,83,10],[84,0,84,7],[85,1,85,10],[86,1,86,10],[87,1,87,10],[88,0,88,4],[88,5,88,10],[91,0,91,10],[92,0,92,1],[92,2,92,10],[93,0,93,1],[93,2,93,6],[93,8,93,10],[94,0,96,0],[94,1,95,1],[94,2,94,6],[94,7,94,10],[95,2,95,6],[95,7,95,10],[96,2,96,10],[97,0,102,0],[97,4,97,6],[98,4,98,6],[98,10,102,10],[99,4,99,6],[100,4,100,6],[101,4,101,6],[102,4,102,6],[103,0,109,0],[104,1,106,1],[110,0,110,7],[111,1,111,10],[112,1,112,10],[113,1,113,10],[114,0,114,4],[114,5,114,10]]}
["附件"]
["部门预算项目支出绩效自评表（2024年度）"]
["项目名称",null,"51042223T000008430576-2022年公共文化服务体系建设"]
["主管部门",null,"盐边县文化广播电视和旅游局（部门）",{"$nulls":4},"实施单位 （盖章）","盐边县文化馆"]
["项目基本情况","1.项目年度目标完成情况","项目年度目标",{"$nulls":4},"年度目标完成情况"]
[null,null,"开展群众文化活动、党的二十大群众文艺活动、群众文体活动、文化培训和图书馆评估定级等工作，提高全县公共文化服务质量。",{"$nulls":4},"开展了第三届艺术节四川群星奖决赛、魅力乡镇竞演暨片区文艺汇演、第八届中国成都国际非遗节美食说唱会、文化和自然遗产日、我们的节日“万人赏月诵秋”演出等活动"]
[null,"2.项目实施内容及过程概述","用于开展了第三届艺术节四川群星奖决赛、魅力乡镇竞演暨片区文艺汇演、第八届中国成都国际非遗节美食说唱会、文化和自然遗产日、我们的节日“万人赏月诵秋”演出等活动，对外宣传盐边，丰富人民群众精神文化生活，提升了全县公共文化服务水平。"]
["预算执行情况（10分）","年度预算数（万元）","年初预算","调整后预算数","预算执行数",null,null,"预算执行率","权重","得分","原因"]
[null,"总额",{"v":2.328,"d":"2.33"},{"v":2.328,"d":"2.33"},{"v":2.328,"d":"2.33"},null,null,{"v":1,"d":"100.00%"},10,10,"1.预算执行率=预算执行数/调整后预算数，预算执行率未达到90%的需说明原因（100字以内）;2.年中发生预算调整的（追加或调减）,应单独说明理由；3.其他资金包括：社会投入资金、银行贷款."]
[null,"其中：财政资金",{"v":2.328,"d":"2.33"},{"v":2.328,"d":"2.33"},{"v":2.328,"d":"2.33"},null,null,{"v":1,"d":"100.00%"},"/","/"]
[null,"财政专户管理资金",{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"单位资金",{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"其他资金",{"$nulls":6},"/","/"]
["绩效指标（90分）","一级指标","二级指标","三级指标","指标性质","指标值","度量单位","完成值","权重","得分","未完成原因分析"]
[null,"产出指标","数量指标","开展群众文体活动","≥","0","场",{"v":1,"d":"100%"},"5",5]
[{"$nulls":3},"开展群众文化活动","≥","5","场",{"v":1,"d":"100%"},"5",5]
[{"$nulls":3},"开展党的二十大群众文艺活动","≥","0","场",{"v":1,"d":"100%"},"5",5]
[{"$nulls":3},"图书馆评估定级","≥","0","项",{"v":1,"d":"100%"},"5",5]
[{"$nulls":3},"文化队伍培训","≥","0","次",{"v":1,"d":"100%"},"5",5]
[null,null,"质量指标","按质量完成","定性","100","%",{"v":1,"d":"100%"},"5",5]
[null,null,"时效指标","2022年—2024年完成","定性","100","%",{"v":1,"d":"100%"},"10",10]
[null,"效益指标","社会效益指标","丰富广大群众精神文化生活，提高全县公共文化服务水平","≥",96,"%","≥96%","20",18]
[null,"满意度指标","服务对象满意度指标","服务对象满意率","≥","96","%","≥96%","10",8]
[null,"成本指标","经济成本指标","开展党的二十大群众文艺活动1场","≥","0","万元",{"v":1,"d":"100%"},"4",4]
[{"$nulls":3},"文化队伍培训1次","≥","0","万元",{"v":1,"d":"100%"},"4",4]
[{"$nulls":3},"开展群众文化活动15场","≥","2.328","万元",{"v":1,"d":"100%"},"4",4]
[{"$nulls":3},"图书馆评估定级1项","≥","0","万元",{"v":1,"d":"100%"},"4",4]
[{"$nulls":3},"开展群众文体活动1场","≥","0","万元",{"v":1,"d":"100%"},"4",4]
["合计",{"$nulls":7},100,96]
["评价结论","通过开展各类活动，对外宣传盐边，丰富人民群众精神文化生活，提升了全县公共文化服务水平。"]
["存在问题","无"]
["改进措施","无"]
["项目负责人：安然",{"$nulls":4},"财务负责人：田尚敏"]
[]
[]
["部门预算项目支出绩效自评表（2024年度）"]
["项目名称",null,"51042224T000010544325-文化馆、图书馆免费开放（民生工程））"]
["主管部门",null,"盐边县文化广播电视和旅游局（部门）",{"$nulls":4},"实施单位 （盖章）","盐边县文化馆"]
["项目基本情况","1.项目年度目标完成情况","项目年度目标",{"$nulls":4},"年度目标完成情况"]
[null,null,"免费开放文化馆和图书馆，每周免费开放时间不少于60小时。文化馆和图书馆年平均接待群众7万余人次，借阅图书8万余册次，每年开展流动服务40余场，基层文化培训辅导20余场，为盐边县精神文明建设提供精神动力和智力支持做出了积极的贡献，不断推动盐边县公共文化服务水平发展。",{"$nulls":4},"免费开放文化馆和图书馆，每周免费开放时间不少于60小时。文化馆和图书馆年平均接待群众7万余人次，借阅图书8万余册次，每年开展流动服务30余场，基层文化培训辅导20余场。"]
[null,"2.项目实施内容及过程概述","保障文化馆、图书馆免费开放。"]
["预算执行情况（10分）","年度预算数（万元）","年初预算","调整后预算数","预算执行数",null,null,"预算执行率","权重","得分","原因"]
[null,"总额",{"v":40,"d":"40.00"},{"v":39.6,"d":"39.60"},{"v":39.6,"d":"39.60"},null,null,{"v":1,"d":"100.00%"},10,10,"1.预算执行率=预算执行数/调整后预算数，预算执行率未达到90%的需说明原因（100字以内）;2.年中发生预算调整的（追加或调减）,应单独说明理由；3.其他资金包括：社会投入资金、银行贷款."]
[null,"其中：财政资金",{"v":40,"d":"40.00"},{"v":39.6,"d":"39.60"},{"v":39.6,"d":"39.60"},null,null,{"v":1,"d":"100.00%"},"/","/"]
[null,"财政专户管理资金",{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"单位资金",{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"其他资金",{"$nulls":6},"/","/"]
["绩效指标（90分）","一级指标","二级指标","三级指标","指标性质","指标值","度量单位","完成值","权重","得分","未完成原因分析"]
[null,"产出指标","数量指标","免费开放文化馆","＝","1","个",{"v":1,"d":"100%"},"10",10]
[{"$nulls":3},"免费开放图书馆","＝","1","个",{"v":1,"d":"100%"},"10",10]
[null,null,"质量指标","严格按质量完成","定性","优",null,{"v":1,"d":"100%"},"10",10]
[null,null,"时效指标","2024年1-12月完成","＝","1","年",{"v":1,"d":"100%"},"10",10]
[null,"效益指标","社会效益指标","丰富广大群众精神文化生活，推动公共文化服务水平不断发展","定性","优",null,{"v":1,"d":"100%"},"20",18]
[null,"满意度指标","服务对象满意度指标","服务对象满意度","≥","96","%",{"v":1,"d":"100%"},"10",8]
[null,"成本指标","经济成本指标","免费开放文化馆","＝","2.4","万元",{"v":1,"d":"100%"},"10",10]
[{"$nulls":3},"免费开放图书馆","＝","2.4","万元",{"v":1,"d":"100%"},"10",10]
["合计",{"$nulls":7},100,96]
["评价结论","提高盐边县公共文化服务水平。"]
["存在问题","无"]
["改进措施","无"]
["项目负责人：安然",{"$nulls":4},"财务负责人：田尚敏"]
[]
[]
[]
[]
[" "]
["项目名称",null,"51042224T000011726465-2024年下坝子考古遗址保护"]
["主管部门",null,"盐边县文化广播电视和旅游局（部门）",{"$nulls":4},"实施单位 （盖章）","盐边县文化馆"]
["项目基本情况","1.项目年度目标完成情况","项目年度目标",{"$nulls":4},"年度目标完成情况"]
[null,null,"对下坝子考古遗址范围内土地进行征收，并划至四至界限进行保护",{"$nulls":4},"遗址保护区域土地问题未解决，后续保护工作无法开展，导致项目未完成"]
[null,"2.项目实施内容及过程概述","遗址保护区域土地问题未解决，导致项目未完成。"]
["预算执行情况（10分）","年度预算数（万元）","年初预算","调整后预算数","预算执行数",null,null,"预算执行率","权重","得分","原因"]
[null,"总额",{"v":0,"d":"0.00"},49.15,49.15,null,null,{"v":0,"d":"0.00%"},10,null,"遗址保护区域土地问题未解决，后续保护工作无法开展"]
[null,"其中：财政资金",{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"财政专户管理资金",{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"单位资金",{"v":0,"d":"0.00"},49.15,49.15,null,null,{"v":1,"d":"100.00%"},"/","/"]
[null,"其他资金",{"$nulls":6},"/","/"]
["绩效指标（90分）","一级指标","二级指标","三级指标","指标性质","指标值","度量单位","完成值","权重","得分","未完成原因分析"]
[null,"产出指标","数量指标","下坝子考古遗址保护","＝","1","项",null,"15",null,"遗址保护区域土地问题未解决，后续保护工作无法开展"]
[null,null,"质量指标","按质量完成","＝","100","%",null,"15"]
[null,null,"时效指标","2024年1-12月完成","＝","1","年",null,"15"]
[null,"效益指标","社会效益指标","保护盐边历史文化遗存","定性","优",null,null,"25"]
[null,"满意度指标","满意度指标","群众满意率","≥","92","%",null,"10"]
[null,"成本指标","经济成本指标","下坝子考古遗址保护1项","＝","49.15","万元",null,"10"]
["合计",{"$nulls":7},100]
["评价结论","无"]
["存在问题","遗址保护区域土地问题未解决"]
["改进措施","无"]
["项目负责人：安然",{"$nulls":4},"财务负责人：田尚敏"]
[]
[]
["部门预算项目支出绩效自评表（2024年度）"]
["项目名称",null,"51042225T000013265479-川财教[2024]61号下达2024年省级文化和旅游发展专项资金（第一批）下达省级非遗代表性传承人补助"]
["主管部门",null,"盐边县文化广播电视和旅游局（部门）",{"$nulls":4},"实施单位 （盖章）","盐边县文化馆"]
["项目基本情况","1.项目年度目标完成情况","项目年度目标",{"$nulls":4},"年度目标完成情况"]
[null,null,"完成对现有4项省级非遗（苗族斗釜歌代表性传承人侯兴友、苗族绷鼓仪式代表性传承人杨华高、仡佬族送年节代表性传承人熊献清、傈僳族婚礼代表性传承人谷万里）项目的保护、传承和展示，每个传承人每年开展传承活动不少于5次。",{"$nulls":4},"2024完成了仡佬族送年节、苗族绷鼓仪式、傈僳族婚礼、苗族斗釜歌4项省级非遗保护项目传承工作，对4名代表性传承人进行了考核，并于2025年第一季度兑现了传承补助。"]
[null,"2.项目实施内容及过程概述","2024完成了仡佬族送年节、苗族绷鼓仪式、傈僳族婚礼、苗族斗釜歌4项省级非遗保护项目传承工作，对4名代表性传承人进行了考核，并于2025年第一季度兑现了传承补助。"]
["预算执行情况（10分）","年度预算数（万元）","年初预算","调整后预算数","预算执行数",null,null,"预算执行率","权重","得分","原因"]
[null,"总额",{"v":0,"d":"0.00"},{"v":2.5,"d":"2.50"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},10,null,"2024年资金下达时已是12月下询，来不及支付，于2025年第一季度完成支付。"]
[null,"其中：财政资金",{"v":0,"d":"0.00"},{"v":2.5,"d":"2.50"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"财政专户管理资金",{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"单位资金",{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},null,null,{"v":0,"d":"0.00%"},"/","/"]
[null,"其他资金",{"$nulls":6},"/","/"]
["绩效指标（90分）","一级指标","二级指标","三级指标","指标性质","指标值","度量单位","完成值","权重","得分","未完成原因分析"]
[null,"产出指标","数量指标","省级非物质文化遗产代表性传承人补助","＝","4","项",null,"10",null,"2024年资金下达时已是12月下询，来不及支付，于2025年第一季度完成支付。"]
[null,null,"质量指标","补助发放率","＝","100","%",null,"20"]
[null,null,"时效指标","补助金发放时间","≤","365","天",null,"20"]
[null,"效益指标","社会效益指标","有力的推进了我县非遗保护工作","定性","效益持续",null,null,"20"]
[null,"满意度指标","服务对象满意度指标","群众满意率","≥","95","%",null,"10"]
[null,"成本指标","经济成本指标","4项省级非物质文化遗产代表性传承人补助","＝","2.5","万元",null,"10"]
["合计",{"$nulls":7},100]
["评价结论","无"]
["存在问题","无"]
["改进措施","无"]
["项目负责人：安然",{"$nulls":4},"财务负责人：田尚敏"]